## Price Proposal
Appendix 2: Price Proposal Template
Document Date | 2023-06-13
Department: | DEPARTMENT OF HOMELESSNESS AND SUPPORTIVE HOUSING
Proposer's Name:
Service Component: | Contract Lifecycle Management System
Instructions: | Proposers shall complete all YELLOW cells in their entirety and bid on all items in this worksheet. Failure to do so will result in a rejected Proposal.
Task 1: Project Initiation and Planning | Task 1 Cost
Subtasks: | 0
1. Project Initiation and Management Plan
2. Regular Project Status Report Planning
3. Configuration/Design/Development/Implementation Plan (if applicable)
4. System Release Plan
5. System Testing Plan
6. Requirements Traceability Plan
7. System Maintenance, Support and Transition Plan
Task 2: Discovery, Analysis, and Design | Task 2 Cost
Subtasks: | 0
1. Discovery Plan, Functional Design Document, Complete Detailed Requirements, Design & Specifications
2. Develop Data Integration Design and Specifications
3. Develop Interface Specifications (if applicable) and Design Document
4. System Architecture and Technical Design
Task 3: Configuration and Development | Task 3 Cost
Subtasks: | 0
1. System Configuration/Development/Implementation
2. Data Integration, Synchronization, and Reporting
Task 4: Testing | Task 4 Cost
Subtasks: | 0
1. Detailed Test Plans
2. Test Scenarios, Test Cases, and Test Scripts
3. Documented System Test Results
Task 5: Project Training | Task 5 Cost
Subtasks: | 0
1. Training Plan
2. Training Manuals, Guides, and Materials
3. Onboarding of Users - Initial Licensing
4. Documented Evidence of Successful End-User Training
Task 6: Deployment | Task 6 Cost
Subtasks: | 0
1. Release Readiness Evaluations and Reports
2. Deployment Plans
3. Migration Plan
4. System Defect Resolution Reports
5. System Documentation
Task 7: Implementation Closeout | Task 7 Cost
Subtasks: | 0
1. Documented Implementation Project Closeout
Project Sub-Total | 0
This amount cannot exceed the project NTE subtotal of $1,000,000
Maintenance and Operations - Annual Budget | Annual Cost
Task 1: System Maintenance | 0
Task 2: Technical Support | 0
Task 3: Hosting Services (if applicable) | 0
Task 4: License Support (if applicable) | 0
Maintenance and Operations Subtotal | 0
The Maintenance and Operations subtotal should be the Applicant's annual estimate. Please refer to Section IIIE, Scope of Work - Overview of Maintenance and Operations Tasks for details regarding each Maintenance and Operations task. Applicant's should use this when proposing their annual cost.
Other Costs
Description | Total Cost
Meetings with HSH (example only) | 0
Miscellaneous (example only) | 0
0
0
0
0
TOTAL OTHER COSTS | 0
Project Total | 0
Maintenance and Operations Total | 0
Other Costs Total | 0
Contract NTE Total | 0